**Accreditation Preparation Timeline - Updated**

|  |  |
| --- | --- |
| January 2015 – May 2015 | Subgroups to draft reports for mock site visit AND design/implement changes to address gaps in standards |
| February 2015 – June 2015 | Accreditation Steering Committee to review reports (see table of draft report due dates) |
| **May 26, 2015** | **Implement any changes to the D3/D4 clinical curriculum for the 2015-2016 academic year** |
| July 1 – August 14, 2015 | Assemble, edit and copy documents for mock site visit |
| **August 3, 2015** | **Implement any changes to the D1/D2 curriculum and the D3/D4 didactic curriculum for the** **2015-2016 academic year** |
| August 17, 2015 | Send documents to mock site visitors |
| **October 5-6, 2015** | **Mock site visit** |
| December 2015 – May 2016 | Implement any additional changes identified during the mock site visit; update, review and finalize documents |
| June – July, 2016 | Assemble, edit and copy documents |
| September 1, 2016 | Send documents to CODA and to site visitors (60 days in advance of the site visit) |
| **November 1-3, 2016** | **Site visit** |